## gahan_saas
At Risk | Task Name | Status | Start Date | End Date | Assigned To | % Complete | Notes
| For help with Gantt Charts in Smartsheet, click to check out the help article. | [5 empty] | Delete this row when you no longer need it.
| SRS (Requirement Specification) | Complete | 2018-08-16 | 2018-08-30 |  | 100%
| Requirement gathering | Complete | 2018-08-16 | 2018-08-06 | Gahan | 100%
| Resource Planning | Complete | 2018-08-16 | 2018-08-07 | Gahan | 100%
| Feasibility Study | Complete | 2018-08-16 | 2018-08-30 | Gahan | 100%
| Prerequisites | Complete | 2018-08-16 | 2018-08-30 | Gahan | 100%
| Prepare SRS document | Complete | 2018-08-16 | 2018-08-30 | Gahan | 100%
| Initial Setup | Complete | 2018-08-18 | 2018-10-07 |  | 25%
| Sprint Planning Meeting | Complete | 2018-08-18 | 2018-08-19 | all teams | 100%
| Set up Backend Environment | Complete | 2018-09-20 | 2018-09-25 | Backend | 100%
| Set up Frontend Environment | Complete | 2018-09-20 | 2018-09-25 | Frontend | 100%
| Construct Basic Prototype | Complete | 2018-09-26 | 2018-10-01 | all teams | 100%
| Testing | Complete | 2018-09-28 | 2018-10-01 | all teams | 100%
| Deployment | Complete | 2018-10-01 | 2018-10-02 | Backend and Frontend | 100%
| Create Prototype | Complete | 2018-10-04 | 2018-10-07 |  | 100%
| Sprint Planning Meeting | Complete | 2018-10-04 | 2018-10-04 | Backend | 100%
| Evaluate existing environment | Complete | 2018-10-04 | 2018-10-05 | Backend | 100%
| Implementation | Complete | 2018-10-05 | 2018-10-13 | all teams | 100%
| Testing | Complete | 2018-10-05 | 2018-10-12 | all teams | 100%
| Deployment | Complete | 2018-10-12 | 2018-10-13 | all teams | 100%
| Integration | Complete | 2018-10-05 | 2018-10-07 |  | 100%
| Sprint Planning Meeting | Complete | 2018-10-05 | 2018-10-05 | core members | 100%
| Integration of Backend and frontend | Complete | 2018-10-05 | 2018-10-05 | all teams | 100%
| Integration | Complete | 2018-10-05 | 2018-10-07 | all teams | 100%
| Testing | Complete | 2018-10-05 | 2018-10-07 | all teams | 100%
| Fixes | Complete | 2018-10-06 | 2018-10-07 | all teams | 100%
| Deployment | Complete | 2018-10-06 | 2018-10-07 | all teams | 100%
| Validation | Complete | 2018-10-05 | 2018-10-07 |  | 100%
| Sprint Planning Meeting | Complete | 2018-10-05 | 2018-10-06 | all teams and client | 100%
| Validation and Verification | Complete | 2018-10-07 | 2018-10-09 | all teams | 100%
| Requirement updation (if needed) | Complete | 2018-10-07 | 2018-10-09 | all teams | 100%
| Feature modification/change/enhancement | Complete | 2018-10-07 | 2018-10-09 | all teams | 100%
| Create Production Release | In Progress | 2018-10-10 | 2018-10-20 |  | 100%
| Sprint Planning Meeting | Complete | 2018-10-10 | 2018-10-11 | all teams | 100%
| Evolution/Implementation of release | In Progress | 2018-10-11 | 2018-10-13 | all teams | 35%
| Implementation | In Progress | 2018-10-13 | 2018-10-18 | all teams | 0%
| Testing | Unassigned | 2018-10-15 | 2018-10-17 | all teams | 0%
| Deployment | Unassigned | 2018-10-16 | 2018-10-18 | all teams | 0%
| Initial Release |  | 2018-10-18 | 2018-11-27 |  | 0%
| Sprint Planning Meeting | TODO | 2018-10-18 | 2018-10-22 | all teams | 0%
| Functionality Testing | TODO | 2018-10-19 | 2018-10-22 | all teams | 0%
| Implementing Non functional aspects | TODO | 2018-10-19 | 2018-10-18 | all teams | 0%
| Ease of use | TODO | 2018-10-19 | 2018-11-24 | all teams | 0%
| Response time | TODO | 2018-10-19 | 2018-10-27 | all teams | 0%
| Scalability | TODO | 2018-11-10 | 2018-10-20 | all teams | 0%
| Security | TODO | 2018-11-17 | 2018-10-22 | all teams | 0%
| Overall Design and Performance | TODO | 2018-11-13 | 2018-10-27 | all teams | 0%