## gahan_saas
At Risk | Task Name | Status | Start Date | End Date | Assigned To | % Complete | Notes
| For help with Gantt Charts in Smartsheet, click to check out the help article. | [5 empty] | Delete this row when you no longer need it.
| SRS (Requirement Specification) |  | 2018-08-16 | 2018-08-30 |  | 100%
| Requirement gathering | Complete | 2018-08-16 | 2018-08-06 | Gahan | 100%
| Resource Planning | Complete | 2018-08-16 | 2018-08-07 | Gahan | 100%
| Feasibility Study | Complete | 2018-08-16 | 2018-08-30 | Gahan | 100%
| Prerequisites | Complete | 2018-08-16 | 2018-08-30 | Gahan | 100%
| Prepare SRS document | Complete | 2018-08-16 | 2018-08-30 | Gahan | 100%
| Initial Setup |  | 2018-08-18 | 2018-11-01 |  | 25%
| Sprint Planning Meeting | Complete | 2018-08-18 | 2018-08-19 | all teams | 100%
| Set up Backend Environment | Complete | 2018-09-20 | 2018-10-10 | Backend | 80%
| Set up Frontend Environment | In Progress | 2018-10-02 | 2018-10-31 | Frontend | 0%
| Construct Basic Prototype | TODO | 2018-10-01 | 2018-11-01 | all teams | 0%
| Testing | TODO | 2018-10-20 | 2018-11-01 | all teams | 0%
| Deadline extension for necessary fixes or changes | TODO | 2018-10-25 | 2018-11-01 | all teams | 0%
| Deployment | TODO | 2018-10-25 | 2018-11-01 | Backend and Frontend | 0%
| Create Prototype |  | 2018-11-01 | 2018-12-10 |  | 0
| Sprint Planning Meeting | TODO | 2018-11-01 | 2018-11-02 | Backend | 0%
| Evaluate existing environment | TODO | 2018-11-02 | 2018-11-05 | Backend | 0%
| Implementation | TODO | 2018-11-06 | 2018-11-30 | all teams | 0%
| Testing | TODO | 2018-11-10 | 2018-12-05 | all teams | 0%
| Deployment | TODO | 2018-12-10 | 2018-12-10 | all teams | 0%
| Integration |  | 2018-12-25 | 2019-01-31 |  | 0
| Sprint Planning Meeting | TODO | 2018-12-25 | 2018-12-27 | core members | 0%
| Integration of Backend and frontend | TODO | 2019-01-01 | 2019-01-10 | all teams | 0%
| Integration | TODO | 2019-01-11 | 2019-01-31 | all teams | 0%
| Testing | TODO | 2019-01-11 | 2019-01-21 | all teams | 0%
| Fixes | TODO | 2019-01-22 | 2019-01-27 | all teams | 0%
| Deployment | TODO | 2019-01-28 | 2019-01-31 | all teams | 0%
| Validation |  | 2019-02-01 | 2019-02-15 |  | 0
| Sprint Planning Meeting | TODO | 2019-02-01 | 2019-02-02 | all teams and client | 0%
| Validation and Verification | TODO | 2019-02-05 | 2019-02-15 | all teams | 0%
| Requirement updation (if needed) | TODO | 2019-02-13 | 2019-02-14 | all teams | 0%
| Feature modification/change/enhancement | TODO | 2019-02-15 | 2019-02-15 | all teams | 0%
| Create Production Release |  | 2019-03-01 | 2019-04-20 |  | 0
| Sprint Planning Meeting | TODO | 2019-03-01 | 2019-03-02 | all teams | 0%
| Evolution/Implementation of release | TODO | 2019-03-03 | 2019-03-25 | all teams | 0%
| Implementation | TODO | 2019-03-20 | 2019-04-10 | all teams | 0%
| Testing | TODO | 2019-04-02 | 2019-04-15 | all teams | 0%
| Deployment | TODO | 2019-04-15 | 2019-04-20 | all teams | 0%
| Initial Release |  | 2019-05-01 | 2019-07-31 |  | 0
| Sprint Planning Meeting | TODO | 2019-05-01 | 2019-05-03 | all teams | 0%
| Functionality Testing | TODO | 2019-05-02 | 2019-05-10 | all teams | 0%
| Implementing Non functional aspects | TODO | 2019-05-02 | 2019-06-30 | all teams | 0%
| Ease of use | TODO | 2019-05-01 | 2019-06-30 | all teams | 0%
| Security | TODO | 2019-05-01 | 2019-06-30 | all teams | 0%
| Response time | TODO | 2019-06-06 | 2019-07-20 | all teams | 0%
| Scalability | TODO | 2019-06-06 | 2019-07-20 | all teams | 0%
| Overall Design and Performance | TODO | 2019-06-06 | 2019-07-20 | all teams | 0%